## Sample EMR plan
NO. |  | ACTIVITY | Output/ Deliverables | Comments | DUR. | START | FINISH | MAR | [22 empty] | APR | [19 empty] | MAY | [22 empty] | JUN | [21 empty] | JUL | [20 empty] | AUG
[8 empty] | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
[8 empty] | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2
Sample Planning - Early Market Research
1 |  | Supply Market Analysis / Desktop Research | Output/ Deliverables | Comments | Duration | Start date | Finish date
ü | 1 | Agency Analysis | bar: MAR W 8
| 2 | [Source of Analysis 2, e.g. AusTender Research ] | bar: MAR W 8
| 3 | [Source of Analysis 3, e.g. Google, stakeholders or colleagues ...] | bar: MAR W 8
| 4 | [Source of Analysis 4] | bar: MAR W 8
| 5 | Finalise Rational for choice of early market research participants | bar: MAR W 8
2 | Early Market Research Documentation
| 1 | Draft questions
| 2 | Finalise questions
| 3 | Finalise Approach - High level overview | bar: MAR W 8
| 4 | Finalise Approach - Detailed | bar: MAR W 8
| 5 | Finalise Participant Invitations
| 6 | Finalise Schedule
3 | Market Sounding Approach
| 1 | Endorsement of early market research received
| 2 | Select early market research Team - ## committed participants
| 3 | Probity briefing and walk through early market research approach
| 4 | Early market research note taker
| 5 | Draft Agenda
| 6 | Participant Escort (if attending in person)
| 7 | Logistics (room Parking, Bookings, Telepresence, Water etc.)
| 8 | Book analyst sessions (e.g. post early market research sessions) + logistics (e.g. rooms, web conferecning if required)
4 | Suppliers Engagement
| 1 | Email inviataions to Suppliers (to schedule meetings at supplier's site allow XX hours in total to inc travel time, etc.)
| 2 | Conduct early market research activity
| 3 | Forrester/Gartner Analyst Session (if appropriate, delete if not)
5 | Market Sounding Round-up
| 1 | Book early market research team for de-brief
| 2 | Prepare draf tearly market research Report
| 3 | Meeting with early market research team to work through draft early market research Report Findings & Recommendations
| 4 | Finalise early market research Findings & Recommendations Report
6 | Deliver Market Sounding Report & Recommendations
| 1 | Issue early market research Findings & Recommendations to Steering Committee (adjust as needed)
| 2 | Present early market research Findings & Recommendations to Steering Committee
Questions?

## Sample brief timeline
| 2019-01-01 |  |  |  | 2019-02-04 |  |  |  | 2019-03-04 |  |  |  | 2019-04-01 |  |  |  |  | 2019-05-06 |  |  |  | 2019-06-03 |  |  |  | 2019-07-01 |  |  |  |  | 2019-08-05 |  |  |  | 2019-09-02 |  |  |  |  | 2019-10-07 |  |  |  | 2019-11-04 |  |  |  | 2019-12-02
 | time axis 2019-01-07 to 2019-12-30
Task <example>
Initial planning and research | bar: 2019-01-07 to 2019-02-25
Development of approach to market documentation | bar: 2019-02-11 to 2019-03-25
Delegate sign-off | bar: 2019-03-25 to 2019-04-01
Documents released to the market | bar: 2019-04-08 to 2019-05-06
Evaluation process conducted | bar: 2019-05-06 to 2019-06-10

## Next Steps (hidden)
Identity and Access Management Procurement - Project Timeline | [53 empty] | Version 1.0 as at: |  |  |  | 2019-09-20 13:19
Objective: Aquire a new IdAM capability for the ATO
WORK PLAN |  | Identity and Access Management Procurement - Project Timeline | [6 empty] | 2019-01-07 |  |  |  | 2019-02-04 |  |  |  | 2019-03-04 |  |  |  | 2019-04-01 |  |  |  |  | 2019-05-06 |  |  |  | 2019-06-03 |  |  |  | 2019-07-01 |  |  |  |  | 2019-08-05 |  |  |  | 2019-09-02 |  |  |  |  | 2019-10-07 |  |  |  | 2019-11-04 |  |  |  | 2019-12-02
Legend: ¿ : Key Milestone ; patterned - task extended
|  |  |  | RACI = Responsible + Accountable + Consulted + Informed |  |  |  | Week begins: | time axis 2019-01-07 to 2019-12-30
Task No |  | Activity | KK/SS | SPC | ATOP | EST | Output/Deliverables | Finish date
1 |  | Develop Procurement Planning and Approach to Market documents
ü | 1 | Market Research and Spend analysis | SS | A |  |  | Finalise Market Research and Internal Spend analysis | 2019-02-22 | [52 empty] | 2019-02-22 | bar: 2019-01-07 to 2019-02-18
| 2 | Develop an initial minute for Megan Boyd | KK | A | C | C | Minute to confirm merging of IB panels | 2019-02-22 | [52 empty] | 2019-02-22 | bar: 2019-02-11 to 2019-03-11
| 3 | Develop Procurement Plan | KK | A | C | C | Finalised Procurement Plan | 2019-03-01 | [52 empty] | 2019-03-01 | bar: 2019-02-11 to 2019-03-11
| 4 | Develop SOR (RFT - part 2) | SS | A | R | R | Finalised SOR | 2019-03-01 | [52 empty] | 2019-03-01 | bar: 2019-02-11 to 2019-03-11
| 5 | Develop Risk Matrix | SS | A | C | C | Finalised Risk Matrix | 2019-03-01 | [52 empty] | 2019-03-01 | bar: 2019-02-18 to 2019-03-11
| 6 | Develop RFT Part 3 - Technical Response Form | SS | A | R | R | Completed Tender Response Document | 2019-03-08 | [52 empty] | 2019-03-08 | bar: 2019-02-18 to 2019-03-11
| 7 | Develop RFT Part 4 - Financial Response Form | SS | A | C | C | Completed Tender Response Document | 2019-03-08 | [52 empty] | 2019-03-08 | bar: 2019-02-18 to 2019-03-11
| 8 | Develop RFT Part 5 - Deed SON for inclusion in tender | SS | A | C | C | Complete DoSO prior to release of Documents | 2019-03-08 | [52 empty] | 2019-03-08 | bar: 2019-02-18 to 2019-03-11
| 9 | Develop RFT Part 1 - Terms of Tender (including Eval Criteria) | SS | A | C | C | Completed Terms and condition of Tender doc | 2019-03-08 | [52 empty] | 2019-03-08 | bar: 2019-02-18 to 2019-03-11
| 10 | Assemble Full Tender Pack | SS | A | C | C | Full Tender Pack Complete | 2019-03-11 | [52 empty] | 2019-03-11 | bar: 2019-03-11
| 11 | Develop Minute for Procurement Plan and SOR | KK | A | I | I | Finalised office minute | 2019-03-18 | [52 empty] | 2019-03-11 | bar: 2019-03-11
| 12 | Submit Procurement Plan and SOR to Megan Boyd for Approval | KK | A | I | I | Endorsement from Megan Boyd to proceed with ATM | 2019-03-21 | [52 empty] | 2019-03-14 | bar: 2019-03-11
| 13 | Procurement Plan Approved |  | I | I | A | Endorsement received from Megan Received | 2019-03-25 | [52 empty] | 2019-03-18 | bar: 2019-03-18 to 2019-03-25
2 |  | Approach to Market
| 1 | Release RFT documentation to Market | SS | A | I | I | Release of Docs on AusTender | 2019-03-27 | [52 empty] | 2019-03-20 | bar: 2019-03-25
| 2 | RFT in market |  | - |  |  | RFT in market - Close 18/04/2019 | 2019-04-22 | [52 empty] | 2019-04-15 | bar: 2019-03-25 to 2019-04-22
| 3 | Industry Briefing Plan | KK/SS | A | C | C | Industry Briefing Plan Complete | 2019-04-03 | [52 empty] | 2019-03-27 | bar: 2019-03-25 to 2019-04-01
| 4 | Conduct Industry Briefing Session | KK/SS | A | C | C | Conduct Industry Briefing Session | 2019-04-04 | [52 empty] | 2019-03-28 | bar: 2019-04-01
| 5 | Clarification questions | SS | A | R | R | Clarify questions from Tenderers | 2019-04-12 | [52 empty] | 2019-04-05 | bar: 2019-04-08
| 6 | Intent to respond due |  | A | I | I | Intent to Respond Received from suppliers | 2019-04-12 | [52 empty] | 2019-04-05 | bar: 2019-04-08
| 7 | Develop Evaluation Plan | SS | A | R | R | Complete Evaluation Planning Document | 2019-04-16 | [52 empty] | 2019-04-09 | bar: 2019-03-25 to 2019-04-15
| 8 | Identify and Confirm Evaluation Panel | KK/SS | A | R | R | Evaluation Panel Member Confirmed | 2019-04-16 | [52 empty] | 2019-04-09 | bar: 2019-04-15
| 9 | Submit Evaluation Plan for Megan Boyd's approval | KK | A | I | R |  | 2019-04-17 | [52 empty] | 2019-04-10 | bar: 2019-04-15
| 10 | Evaluation Plan Approved |  | I | I | R | Approval | 2019-04-17 | [52 empty] | 2019-04-12 | bar: 2019-04-15
| 11 | Approach to Market Closes |  | A | I | I | Receive Tenders from applicants | 2019-04-18 | [52 empty] | 2019-04-15 | bar: 2019-04-15
3 |  | Evaluation Process
| 1 | Review Tenders and Conduct Compliance Checks | SS | A | I | I | Non-compliant tenders culled | 2019-04-26 | [52 empty] | 2019-04-19 | bar: 2019-04-22
| 2 | Probity Briefing for Evaluation Team | SS/KK |  |  |  |  | 2019-04-25 | [52 empty] | 2019-04-18 | bar: 2019-04-22
| 3 | Evaluation Team to conduct Technical Evaluation of Remaining Tenderers |  | I | A | A | All Responses Rated and Successful Tenderers Identified | 2019-05-18 | [52 empty] | 2019-05-11 | bar: 2019-04-29 to 2019-05-13
| 4 | Financial evaluation conducted on shortlisted tenderers | SS | A | I | I | All Remaining Responses Rated and Successful Tenderers Identified | 2019-05-18 | [52 empty] | 2019-05-11 | bar: 2019-04-29 to 2019-05-13
| 5 | Reviewing Tenders for Risks | SS/KK | A | R | R | Confirm Compliance with Risks | 2019-05-18 | [52 empty] | 2019-05-11 | bar: 2019-05-13
| 6 | Evaluation Report developed | KK/SS | A | A | A | Complete Evaluation Report | 2019-05-25 | [52 empty] | 2019-05-18 | bar: 2019-05-13 to 2019-05-20
| 7 | Evaluation and Outcomes report Submitted to Megan Boyd For Approval | KK/SS | A | I | I | Report evaluation outcomes and seek approval to progress to negotiation | 2019-05-25 | [52 empty] | 2019-05-18 | bar: 2019-05-20
| 8 | Evaluation Report Approved |  | I | I | R | Achieve Endorsement of Preferred Suppliers to progress to negotiation | 2019-05-30 | [52 empty] | 2019-05-23 | bar: 2019-05-27
4 |  | Negotiation Stage - Process TBC
| 1 | Develop Negotiation Plan | TBA | A | C | C | Finalised Draft Negotiation Plan | 2019-05-25 | [52 empty] | 2019-05-18 | bar: 2019-05-06 to 2019-05-20
| 2 | Notify preferred Tenderers of Intent to negotiate | TBA |  |  |  | Emails Sent | 2019-06-01 | [52 empty] | 2019-05-25 | bar: 2019-05-27
| 3 | Conduct Negotiation with Preferred Suppliers | TBA | A | R | R | Establish standardised Terms and Conditions and harmonised Rates across all Preferred Suppliers | 2019-06-07 | [52 empty] | 2019-05-31 | bar: 2019-05-27 to 2019-06-03
| 4 | Develop Negotiation Outcomes Report | TBA | A | R | R | Complete Negotiation Outcome Report | 2019-06-15 | [52 empty] | 2019-06-08 | bar: 2019-06-10
| 5 | Negotiation Outcomes Report submitted to Megan Boyd for Approval | TBA | A | I | I | Achieve Endorsement of Successful Suppliers | 2019-06-17 | [52 empty] | 2019-06-10 | bar: 2019-06-17
| 6 | Establish Contracts with Successful Suppliers | TBA | A | C | C | Achieve Deeds of Standing Offers | 2019-06-22 | [52 empty] | 2019-06-15 | bar: 2019-06-17 to 2019-06-24
5 |  | Panel Transition - Process TBC
| 1 | Identify Contractors needing to transition to new providers | TBA | C | A | A | Contractors for transition identified - transition will occur progressively as WO's expire. | Ongoing | [52 empty] | Ongoing | bar: 2019-08-19 to 2019-11-04
| 2 | Conduct Panel introduction meetings | TBA | A | R | R |  | 2019-08-26 | [52 empty] | 2019-08-19 | bar: 2019-08-19 to 2019-08-26
| 3 | Conduct Unsuccessful feedback | TBA | A | R | R | Unsuccessful Supplier Feedback completed | 2019-09-16 | [52 empty] | 2019-09-09 | bar: 2019-08-19 to 2019-09-16